## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | As a customer-account executive /cashier / teller I want to be able to log in the bank website with my user ID and password So that I carry out my transactions | Task 1 | Shubham Kumar Tiwari | Create API for login functionality | 4 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template for login page | 4 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field for login functionality | 3 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing of login page | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
US002 | As a customer-account executive I want to be able to capture new customer information So that I can create a new customer in the system | Task 1 | Shubham Kumar Tiwari | Create API for new customer functionality | 3 | 1 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template for new customer page | 3 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field for new customer functionality | 4 | 1 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing of new customer page | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
US003 | As a customer-account executive I want to be able to edit existing customer information So that I can store the updated customer information in the system | Task 1 | Shubham Kumar Tiwari | Create API to update existing customer functionality | 5 | 4 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template for update existing customer page | 4 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field to update existing customer functionality | 5 | 4 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing of updated existing customer page | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
US004 | As a customer-account executive I want to be able to delete existing customer from system | Task 1 | Shubham Kumar Tiwari | Create API for deletion of existing customer functionality | 4 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template for deletion of existing customer page | 5 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field for deletion of existing customer functionality | 3 | 3 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing of deleted existing customer page | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
US005 | As a customer-account executive I want to be able to view the status of all the customers of the bank | Task 1 | Shubham Kumar Tiwari | Create API to view the status of all customer functionality | 4 | 4 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template to view the status of all customer page | 4 | 4 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field to view the status of all customer functionality | 3 | 2 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing of status of all customer page | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Closed
US006 | As a customer-account executive I want to be able to capture account details So that I can create a new bank account for an existing customer | Task 1 | Shubham Kumar Tiwari | Create API to capture account detail of existing customer functionality | 4 | 4 | 4 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template to capture account detail of existing customer page | 4 | 3 | 3 | 3 | 0 | 0 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field to capture account detail of existing customer functionality | 3 | 3 | 3 | 3 | 0 | 0 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing to capture account detail of existing customer page | 2 | 2 | 2 | 1 | 0 | 0 | 0 | Closed
US007 | As a customer-account executive I want to be able to delete an account of an existing customer | Task 1 | Shubham Kumar Tiwari | Create API to delete an account of an existing customer functionality | 3 | 3 | 3 | 3 | 2 | 0 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template to delete an account of an existing customer page | 4 | 4 | 4 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field to delete an account of an existing customer functionality | 3 | 3 | 3 | 1 | 0 | 0 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing to delete an account of an existing customer page | 2 | 2 | 2 | 1 | 1 | 0 | 0 | Closed
US008 | As a customer-account executive I want to be able to view the status of all the accounts of the bank | Task 1 | Shubham Kumar Tiwari | Create API to view the status of all the accounts functionality | 5 | 5 | 5 | 3 | 0 | 0 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template to view the status of all the accounts page | 4 | 4 | 4 | 2 | 0 | 0 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field to view the status of all the accounts functionality | 3 | 3 | 3 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing to view the status of all the accounts page | 2 | 2 | 2 | 1 | 0 | 0 | 0 | Closed
US009 | As a customer-account executive I want to be able to search for a customer So that I am able to view the details | Task 1 | Shubham Kumar Tiwari | Create API for searching through customer id functionality | 4 | 4 | 4 | 2 | 2 | 0 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template for searching through customer id page | 3 | 3 | 3 | 1 | 0 | 0 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field for searching through customer id functionality | 3 | 3 | 3 | 1 | 0 | 0 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing of searched through customer id functionality | 2 | 2 | 2 | 2 | 1 | 0 | 0 | Closed
US010 | As a Cashier/ Teller I want to be able to search for a bank account So that I am able to view the details | Task 1 | Shubham Kumar Tiwari | Create API for searching through bank account functionality | 3 | 3 | 3 | 2 | 0 | 0 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template for searching through bank account page | 4 | 4 | 4 | 3 | 1 | 0 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field for searching through bank account functionality | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing of searched through bank account functionality | 3 | 3 | 3 | 3 | 1 | 0 | 0 | Closed
US011 | As a Cashier/ Teller I want to be able to deposit money into a customer's account So that I am able to service the customer's request | Task 1 | Shubham Kumar Tiwari | Create API for deposite money functionality | 4 | 4 | 4 | 4 | 0 | 0 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template for deposite money page | 4 | 4 | 4 | 4 | 2 | 0 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field for deposite money functionality | 5 | 5 | 5 | 5 | 4 | 2 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing of deposited money functionality | 2 | 2 | 2 | 2 | 1 | 1 | 0 | Closed
US012 | As a Cashier/ Teller I want to be able to withdraw money from a customer's account So that I am able to service the customer's request | Task 1 | Shubham Kumar Tiwari | Create API for withdraw money functionality | 5 | 5 | 5 | 5 | 5 | 2 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template for withdraw money page | 5 | 5 | 5 | 5 | 4 | 2 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field for withdraw money functionality | 4 | 4 | 4 | 4 | 4 | 2 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing of withdraw money functionality | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Closed
US013 | As a Cashier/ Teller I want to be able to transfer money from a customer's account So that I am able to service the customer's request | Task 1 | Shubham Kumar Tiwari | Create API for transfer money functionality | 5 | 5 | 5 | 5 | 5 | 3 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template for transfer money page | 5 | 5 | 5 | 5 | 5 | 2 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field for transfer money functionality | 4 | 4 | 4 | 4 | 4 | 1 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing of transfered money functionality | 2 | 2 | 2 | 2 | 2 | 1 | 0 | Closed
US014 | As a Cashier/ Teller I want to be able to print an account statement So that I am able to service the customer's request | Task 1 | Shubham Kumar Tiwari | Create API to print transaction functionality | 4 | 4 | 4 | 4 | 4 | 2 | 0 | Closed
|  | Task 2 | Shubham Singh Rathore | Design template to print transaction page | 4 | 4 | 4 | 4 | 4 | 3 | 0 | Closed
|  | Task 3 | Shakeeb Arsalan | Create database field to print transaction functionality | 4 | 4 | 4 | 4 | 4 | 0 | 0 | Closed
|  | Task 4 | Sachin kumar | Create test cases for unit testing of print transaction functionality | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Closed
|  |  |  | Total | 192 | 160 | 128 | 96 | 64 | 32 | 0

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
192 | 170 | 130 | 95 | 60 | 25 | 0
192 | 160 | 128 | 96 | 64 | 32 | 0